## Sheet1
Task | Assigned Member | Take description | Workload(Difficulty) (1 =easy, 5 = hard) | Tester | Completion date
Set up repository | Cleon Haung | Create a repository on GitHub and add teammate | 1 | Aloysius Porter Zadro | 2023-10-18
Create unity project | Cleon Haung | Create a unity project in the main branch of the repo (with gitignore) | 1 | Aloysius Porter Zadro | 2023-10-18
ERD design | Cleon Haung, Aloysius Porter Zadro | Designing the code architecture. | 4 |  | 2023-10-28
Level maps (10%) | Aloysius Porter Zadro | Implement code and designing level | 2 | Cleon Haung
Physics-based ball movement (5%) | Cleon Haung | Implement code | 1 | Aloysius Porter Zadro
Player movement (25%) | Cleon Haung | Implement code | 5 | Aloysius Porter Zadro
Kicking the ball (15%) | Aloysius Porter Zadro | Implement code | 3 | Cleon Haung
Goal (5%) | Cleon Haung | Implement code | 1 | Aloysius Porter Zadro
Player animation (5%) | Cleon Haung | Implement code | 1 | Aloysius Porter Zadro
Camera control (15%) | Aloysius Porter Zadro | Implement code | 3 | Cleon Haung
User interface (10%) | Aloysius Porter Zadro | Implement code | 2 | Cleon Haung
Analytics (10%) | Cleon Haung | Implement code | 2 | Aloysius Porter Zadro
QA plan | Cleon Haung | Creating tests | 2 | Aloysius Porter Zadro
Bug history | Cleon Haung, Aloysius Porter Zadro | Recording bugs | 3 | Cleon Haung, Aloysius Porter Zadro
Data Management Plan | Aloysius Porter Zadro | Documenting data management | 2 | Cleon Haung
Git Version Control | Cleon Haung, Aloysius Porter Zadro | Checking git repos, and eachothers. | 1 | Cleon Haung, Aloysius Porter Zadro